## Simple Gantt Chart - EX
PROJECT TITLE | Minesweeper: Fantasy Edition
PROJECT MANAGER | Prachee Nanda
COURSE | ICS4UE-21
DATE | 2020-08-22
GANTT CHART |  |  |  |  | PROPOSAL | FEASIBILITY STUDY |  | PROJECT DEVELOPMENT |  |  | TESTING
TASK | TASK | START | DUE | DURATION (IN HOURS) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
1 | Project Proposal
1.1 | Scope Document | 2020-08-19 | 2020-08-19 | 4
2 | Feasibility Study
2.1 | Problem Definition and Analysis | 2020-08-20 | 2020-08-20 | 4
2.2 | End User Requirements | 2020-08-20 | 2020-08-20 | 4
2.3 | Software Project Plan | 2020-08-20 | 2020-08-21 | 16
2.3.1 | Resource List | 2020-08-20 | 2020-08-20 | 4
2.3.2 | Gantt Chart | 2020-08-20 | 2020-08-21 | 4
2.3.3 | Flowchart/UML Diagrams | 2020-08-20 | 2020-08-21 | 8
2.4 | Review | 2020-08-21 | 2020-08-21 | 12
3 | Project Development
3.1 | Developing Opening/Game Over Screen | 2020-08-22 | 2020-08-22 | 12
3.2 | Developing Minesweeper Game | 2020-08-22 | 2020-08-24 | 60
3.2.1 | Create original version | 2020-08-22 | 2020-08-23 | 36
3.2.2 | Create personal enhancements (e.g. graphics) | 2020-08-23 | 2020-08-24 | 24
4 | Testing and Verification
4.1 | Test Software Program | 2020-08-24 | 2020-08-25 | 24